## Main
<Skeleton Party>
<Skeleton Party>
<Skeleton Party>
Project Start | 4449400%
Project Status | GREEN
Comments
|  |  | Hours |  |  |  |  | 4450100% |  | 4450800% |  | 4451500% |  | 4452200% |  | 4452900%
Student Name | Student DigiPen e-mail | Average Committed Weekly Hours | Done | In Progress | Not Started | Total Workload | Planned Code % | Workload | Remaining | Workload2 | Remaining3 | Workload4 | Remaining5 | Workload6 | Remaining7 | Workload8 | Remaining9
Isaac yeo | i.yeo@digipen.edu | 10 | 10 | 15 | 0 | 25 | 136% | 10 | 0 | 10 | -10 | 10 | -11 | 10 | -12 | 10 | -12
Jazz Yu Jue TEOH | j.teoh@digipen.edu | 10 | 10 | 19 | 5 | 34 | 147.1% | 10 | 0 | 10 | 0 | 10 | -20 | 10 | -20 | 10 | -20
Yi Thon GOH | yithon.goh@digipen.edu | 10 | 10 | 0 | 0 | 10 | 200% | 10 | 0 | 10 | -10 | 10 | -10 | 10 | -14 | 10 | -14
Qiu Hui TAN | qiuhui.tan@digipen.edu | 10 | 10 | 0 | 8 | 18 | 105.6% | 10 | 0 | 10 | -10 | 10 | -10.5 | 10 | -11.5 | 10 | -11.5
Wei Jie Keith LUA | weijiekeith.lua@digipen.edu | 10 | 10 | 20 | 13.5 | 43.5 | 116.1% | 10 | -10 | 10 | -10 | 10 | -10 | 10 | -11 | 10 | -11
|  |  | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team Totals : | 50 | 50 | 54 | 26.5 | 130.5 | #DIV/0! | 50 | -10 | 50 | -40 | 50 | -61.5 | 50 | -68.5 | 50 | -68.5

## GANTT
<Skeleton Party> | [15 empty] | Enter "Spacer" in column A to create a space
Project Start | [5 empty] | 4448700%
Week Offset | [5 empty] | 1
Made in DigiPen | [15 empty] | 357 |  | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29
TASK | TASK TYPE | PRIORITY | EPIC | TASK DESCRIPTION | ESTIMATED HOURS | ASSIGNEE | PLANNED START | PLANNED DAYS | PLANNED END | Grade | Perceived Hours | Feedback | ACTUAL START | ACTUAL DAYS | ACTUAL END | ACTUAL HOURS | STATUS | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05
[18 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Player Controls(WASD Movement) | Code | 1. Must Have | Controls | player should be able to move in the 4 cardinal directions, at a constant speed | 10 | Qiu Hui TAN | 4449400% | 2 | 4449600% |  | 5 |  | 4449400% | 2 | 4449600% | 11 | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
player collision | Code | 1. Must Have | Collision | When the player collide with enemy, player should take damage | 10 | Wei Jie Keith LUA | 4449400% | 2 | 4449600% |  | 5 |  | 4449400% | 2 | 4449600% | 10 | Completed
enemy collision | Code | 1. Must Have | Collision | Enemy health and collision detection from attacks | 10 | Yi Thon GOH | 4449400% | 2 | 4449600% |  | 15 |  | 4449400% | 5 | 4449900% | 15 | Completed
player and enemy health ui | Code | 2. Should Have | Rendering | instance a heart based health system for the player. When the player is hit, 1 heart is deduted, and when the player is healed, one heart is added. The player cannot heal beyond the declared max hearts | 10 | Isaac yeo | 4449400% | 2 | 4449600% |  | 10 |  | 4449400% | 3 | 4449700% | 14 | Completed | 1 | i.yeo@digipen.edu <i.yeo@digipen.edu>; | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
menu & base screen | Code | 1. Must Have | Rendering | Menu interface (includes play/menu button) and game background | 10 | Wei Jie Keith LUA | 4449400% | 2 | 4449600% |  | 5 |  | 4449400% | 4 | 4449800% | 10 | Completed
melee swing attack | Code | 1. Must Have | physics | Player able to do melee attack in a cone shape infront of them | 10 | Jazz Yu Jue TEOH | 4449400% | 2 | 4449600% |  | #N/A |  | 4449400% | 2 | 4449600% | 15 | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spacer |  |  |  |  | 4 |  |  | 3 | 300% |  | #N/A |  | 4432800% | 2 | 4433000% |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enemy Movement/Behaviour | Code | 1. Must Have | physics | Enemy moving with patterns. Naming a few, enemy moving horizontally, diagonally, spirally, back and forth and finally wavey. | 10 | Jazz Yu Jue TEOH | 4450100% | 4 | 4450500% |  | 10 |  | 4450300% | WIP | #VALUE! | WIP | In Progress | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Integration of Enemy instancing, collision, Enemy Movement, Enemyspawn | Bug Fix | 1. Must Have | Rendering | integrate the work from a few members so the functions declared by other members can run seamlessly. Integration of tack include Enemy movemnt behaviour,spawning of enemies.maybe include collision checks |  | Isaac yeo | 4450400% | 4 | 4450800% |  | 10 |  | 4451000% | 7 | 4451700% | 10 | Completed | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spawning/Game Level System. Enemy movement | Code | 1. Must Have | Rendering | create a function to print the enemysprite art where the enemy is, create a function that can move the enemy across the screen, create a system of arrays to store information on each enemy spawned. Create a spawn map that will spawn in enemies | 15 | Isaac yeo | 4450100% | 4 | 4450500% |  | 6 |  | 4449900% | 3 | 4450200% | 15 | In Progress | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
enemy sprite art | Art | 2.Should Have | Rendering | create a sprite for the enemy | 10 | Isaac yeo | 4450100% | 1 | 4450200% |  | 2 |  | 4450100% | 1 | 4450200% | 2 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Knight , Mage, Archer image art | art | 1. Must Have | Rendering | create sprite image for 3 character |  | Qiu Hui TAN | 4450200% | 3 | 4450500% |  | 5 |  | 4450200% | 2 | 4450400% | 5 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Background 1 | Art | 3.Could Have | Rendering | create background image for game | 10 | Qiu Hui TAN | 4450400% | 1 | 4450500% |  | 1 |  | 4450200% | 1 | 4450300% | 1 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pause UI | Code | 1. Must Have | Rendering | Create function that will change game state from play to pause and when esc ¦¦ pause key is pressed, and Change gamestate from pause to play when play ¦¦ continue button is pressed | 10 | Yi Thon GOH | 4450100% | 1 | 4450200% |  | 1 |  | 4450600% | 1 | 4450700% | 5 | Completed
level design (1-5 levels) | Code | 1. Must Have | Gameplay | Making levels with set amount of enemy movements | 5 | Jazz Yu Jue TEOH | 4450400% | 1 | 4450500% |  | 5 |  | 4450600% | WIP | #VALUE! | WIP | In Progress
Game State Logic | Code | 3.Could Have | Gameplay | Transition between game states of main menu, pause, playing, exit, etc | 10 | Wei Jie Keith LUA | 4450100% | 1 | 4450200% |  | 5 |  | 4450200% | WIP | #VALUE! | WIP | In Progress
Enemy Drops (chance to drop, maybe hp, basics) | Code | 2.Should Have | Gameplay | Enemy drops include healing items, temporary buffs,etc | 10 | Wei Jie Keith LUA | 4450400% | 1 | 4450500% |  | 5 |  | 4450700% | 1 | 4450800% | 5 | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spacer | [8 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story progression | level | 1. Must Have | Rendering | making of dialogue boxes/introduction player to game | 0.5 | Qiu Hui TAN | 4451000% | 1 | 4451100% |  | 3 |  | 4451000% | 1 | 4451100% | 4 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Skill System/Tree and Menus Ui | Code | 4. Won't Have | Gameplay/Rendering | lets the players enchance the stats of the knight and mage, and max hp, etc . Make Menu Ui for skill Tree that involes changing gamestates, intergrate with exp and drops. Display amount of exp and money the player has accumutaed. Make a working shop that will deduct gold and unlock certain game features. Make art for menu with working buttons to navigate. | 1 | Isaac yeo | 4451300% | 2 | 4451500% |  | 10 |  | 4451200% | 4 | 4451600% | 25 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Second Weapon (Character Switching) | Code | 1. Must Have | Rendering | Swich between the knight and the mage classes |  | Isaac yeo | 4451100% | 2 | 4451300% |  | 10 |  | 4451200% | 1 | 4451300% | 4 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd Weapon code (mage) | Code | 3. Could Have | Collision | Mage's explosion attack with all skills tree features implemented | 15 | Jazz Yu Jue TEOH | 4450800% | 4 | 4451200% |  | 15 |  | 4450900% | 4 | 4451300% | 13 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st Weapon skills feature | Code | 1. Must Have | Collision | knights melee attack features and upgrades | 5 | Jazz Yu Jue TEOH | 4451000% | 2 | 4451300% |  | 5 |  | 4451300% | 1 | 4451400% | 4 | Completed
2nd Enemy idea & Sprite Design | Art | 2. Should Have | Rendering | Second Enemy Sprite |  | Isaac yeo | 4450800% | 1 | 4450900% |  | 2 |  | 4450800% | 1 | 4450900% | 2 | Completed
Updated Paue UI | Art | 3. Could Have | Rendering | make art for pause screen that will be dispayed when game state is changed to pause |  | Yi Thon GOH | 4451000% | 2 | 4451100% |  | 5 |  | 4451200% | 2 | 4451400% | 3 | Completed
2nd Weapon idea & Sprite Design (Mage) | Art | 2. Should Have | idea | Design of mage sprite and weapon code |  | Yi Thon GOH | 4451000% | 1 | 4451100% |  | 5 |  | 4452000% | 1 | 4452100% | 1 | Completed
1st Enemy idea & Sprite Design | Art | 1. Must Have | Rendering | First Enemy Sprite |  | Isaac yeo | 4450900% | 1 | 4451000% |  | 2 |  | 4450900% | 1 | 4451000% | 2 | Completed
Enemy Drop continuation | Code | 1. Must Have | Rendering | Continue on designing and programming the enemy drops |  | Wei Jie Keith LUA | 4450800% | 4 | 4451100% |  | 10 |  | 4451400% | 2 | 4451600% | 4 | Completed
Update Main Menu Design | Art | 1. Must Have | Rendering | Updated the main menu design |  | Wei Jie Keith LUA | 4450800% | 1 | 4451200% |  | 5 |  | 4451300% | 2 | 4451500% | 5 | Completed
Second enemy | Code | 1. Must Have | Rendering | Second enemy movement | 1.5 | Wei Jie Keith LUA | 4451200% | 1 | 4451300% |  | 5 |  |  |  | 0% |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spacer | [8 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
enemey movement |  | 1. Must Have | Gameplay | the way the enemy is programed to move |  | Qiu Hui TAN | 4451500% | 1 | 4451600% |  | 2 |  | 4451600% | 1 | 4451600% | 3 | Completed
level design | Code | 1. Must Have | rendering | making level with enemy | 1 | Qiu Hui TAN | 4451500% | 3 | 4451800% |  | 8 |  | 4451800% | 4 | 4452200% | 7 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprite art & animation | Art | 4. Won't Have | idea | draw the sprite for the archer weapon and animation for the archer's attack | 1 | Isaac yeo | 4451500% | 1 | 4451600% |  | 5 |  | 4451800% | 2 | 4452000% | 3 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3rd Weapon idea & Sprite (archer) | Art | 3. Could Have | idea | come up with the concept for the archer | 4 | Isaac yeo | 4454800% | 2 | 4455000% |  | 2 |  | 4451700% | 1 | 4451800% | 5 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3rd Weapon code (archer) | Code | 3. Could Have | Gameplay | program the physics for the archer's attack | 4 | Jazz Yu Jue TEOH | 4451500% | 3 | 4451800% |  | 10 |  | 4452000% | 2 | 4452200% | 5 | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Music/SoundEffects | Code | 3. Could Have | Rendering | implementing audio and is able to trigger it |  | Yi Thon GOH | 4452000% | 5 | 4452500% |  | 5 |  | 4452000% | 1 | 4452100% | 4 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Music | Audio | 3. Could Have | Rendering | music composition | 4 | Yi Thon GOH | 4451500% | 3 | 4451800% |  | 5 |  | 4451100% | 2 | 4451300% | 7 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound Effects | Audio | 3. Could Have | Rendering | sound effects, trigggered when collision or something on screen happen | 4 | Yi Thon GOH | 4454800% | 2 | 4455000% |  | 5 |  | 4451900% | 2 | 4452100% | 7 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Player Invulerability Frame |  | 2. Should Have | Gameplay | after taking damage, the player will be invunerable to damage for a short duration |  | Wei Jie Keith LUA | 4451500% | 1 | 4451500% |  | 7 |  | 4452000% | 1 | 4452100% | 9 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Player Character customisation | Code | 2. Should Have | Gameplay | allows the player to change the spirte between the knight, mage and archer | 1 | Wei Jie Keith LUA | 4451500% | 4 | 4451900% |  | 5 |  | 4452000% | 1 | 4452100% | 2 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spacer | [8 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop System with Art | Code | 1. Must Have | Rendering | lets the players buy the additional perks to enhance skill and modify the game, etc . Make Menu Ui for shop that involes changing gamestates, intergrate with and gold drops, extra skills, extra lives and double drop chance | 8 | Isaac yeo | 4452200% | 2 | 4452400% |  | 4 |  | 4452000% | 2 | 4452200% | 10 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Save System | Code | 2. Should Have | Gameplay | allows the player to save their progress when returning to main menu | 8 | Wei Jie Keith LUA | 4452200% | 3 | 4452500% |  | 5 |  |  |  | 0% |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enemy with simple projectile | Code | 2. Should Have | Rendering | specific types of enemies will fire a projectile at the player | 8 | Qiu Hui TAN | 4452200% | 1 | 4452300% |  | 10 |  |  |  | 0% |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Knight melee knockback | Code | 2. Should Have | physics | when the enemy is hit with a sword, they get knocked back | 1 | Jazz Yu Jue TEOH | 4452200% | 1 | 4452300% |  | 10 |  |  |  | 0% |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spacer | [8 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Playtesting | Art | 3. Could Have |  |  | 4 | Jazz Yu Jue TEOH | 4452900% | 4 | 4453300% |  | #N/A |  |  |  | 0% |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Debugging | Audio | 3. Could Have |  |  | 4 | Wei Jie Keith LUA | 4452900% | 4 | 4453300% |  | #N/A |  |  |  | 0% |  | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Audio | 3. Could Have |  |  | 4 |  |  |  | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0% |  | #N/A |  |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Priorities
Priorities | Brief
1. Must Have | Critical, cannot do without
2. Should Have | Important to the project but not vital
3. Could Have | Nice to have
4. Won't Have | Would not contribute to your project, can do without

## TaskTypes
Task Types | Description & Requirements | Requirements
Level | For tasks related to creating levels for the project. Ideally done without hardcoding all objects in the level within code. | @Must have a beginning and an end @Meaningful choices for the player to make @Clear objective
Art | For tasks related to creating visual art assets for the project. This includes fonts. Fonts : There are some license free fonts allowed for use. Refer to forum post. This should be kept to a minimum for RTIS and IMGD students. | @Refer to the EULA that you signed at the start of the semester @Do not use existing art assets even if they are "license free" @Tools used in the generation of art assets must be license and cost free
Audio | For tasks related to finding, creating and/or getting audio assets into the project. There are audio assets provided by the school via MetaDigger. Refer to forum post. The tasks related to coding an audio system to play audio assets should be under "Code". The audio system is a coded feature. | @Refer to the EULA that you signed at the start of the semester @Usage of existing audio assets allowed only for those found in the school's MetaDigger @Do not use external existing audio assets even if they are "license free", provided for or generated by tools @Recording your own audio, editting it with a free tool and using that asset is allowed
Code | For tasks related to feature implementation and code integration. Hardcoding levels and content for the game does not fall under this category. That would be under the task type of "Level" | @Feature functions as described and intended @No crashes, warnings, errors from implementation @Does not break existing features. If it does, those breaks should be fixed for this task to be done
Bug Fix | For tasks related to fixing bugs that have been detected. Debugging is expected to be done during coding and development, but not all bugs would get detected during that phase. | @Symptoms identified with bugs gone @No crashes, warnings, errors from implementation @Does not break existing features. If it does, those breaks should be fixed for this task to be done
Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | #VALUE! | #VALUE!
Code | Player Controls(WASD Movement): player should be able to move in the 4 cardinal directions, at a constant speed | must have
Code | player collision : When the player collide with enemy, player should take damage | must have
Code | enemy collision : Enemy health and collision detection from attacks | must have
Art/ code | player and enemy health ui: instance a heart based health system for the player. When the player is hit, 1 heart is deduted, and when the player is healed, one heart is added. The player cannot heal beyond the declared max hearts | must have
Code | menu & base screen: Menu interface (includes play/menu button) and game background | must have
Code | melee swing attack : Player able to do melee attack in a cone shape infront of them | must have
Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | Spacer | #VALUE! | #VALUE!
Code | Enemy Movement/Behaviour: Enemy moving with patterns. Naming a few, enemy moving horizontally, diagonally, spirally, back and forth and finally wavey. | must have
Code | Spawning/Game Level System. Enemy movement, enemy sprite art : spawn the enemy in 3 different patterns at random location. The enemy will travel towards the player at a set velocity. Enemy sprite will be made as well | must have
art | Enemy 1 Sprite Placeholder : image/shape of enemy to be created | should have
art | Background 1 : drawing of game background | could have
Code | Pause UI: Pause screen ,User interface for player (from continue to restart?) | must have
Code | level design (1-5 levels) : Making levels with set amount of enemy movements | must have
Code | Game State Logic : The game state machine should be able to transit from paused to play to the various menus. | could have
Code | Enemy Drops (chance to drop, maybe hp) : When enemy die, there a probabiltiy that it will drop/spawn items that will give the player a buff or heal him | should have

## TaskGrading (hidden)
Brief | Grades here denote the perceived complexity of the task by the lecturer. This perception is based on expectations of the students' education so far from this semester. Estimated work hours stated here reflect what the lecturer perceives as the time required to complete by the student based on the education received so far.
Grade | Description | Estimated Work Hours
A | An advance task that requires self-study, using techniques not taught in class, a great challenge for the student at this current stage of education. | 8
B | A task within the ability expected of students, an advance application and usage of what has been taught. Students should be able to complete | 5
C | A basic task that the student should be able to complete in 2 hours or less. | 2
F | Unable to discern what the task is. Task is poorly defined. Task is too big to be useful. | 0

## TaskStatus
Status | Description
Not Started | Task is/will be completed and in the final product
In Progress | Being worked on. Includes testing and debugging
Completed | Done, in working order.

## ProjectStatus
Colour | Description
RED | More than a week behind. Having multiple difficulties. Some problems impeding or halting progress. Need help. | If your Team is experiencing any problems, do write it down in the comments below your project status
YELLOW | One week Behind
GREEN | Ahead or on time